## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Setup project environment (downloaded jdk 17 and intellij, made github repo) | MUST HAVE |  | All Students | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Implement Product model & InventoryManager with OOP and stored data in hashmap + Exception Handling | MUST HAVE | US-1 | All Students | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Implement persistence with CSV & Git workflow | MUST HAVE | US-1,US-2 | All Students | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Database basics: SQL practice + JDBC connection test | MUST HAVE |  | All Students | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Implement Read Operations (getAll, getById) & Console Menu Integration | MUST HAVE | US-4 | All Students | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Implement Update & Delete Operations | MUST HAVE | US-4 | All Students | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Integrate CRUD into Console Menu (End-to-End Test) | MUST HAVE | US-5+US-6 | All Students | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Add Input Validation & Error Handling | MUST HAVE |  | All Students | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Junit testing | MUST HAVE | ALL US | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Implement CSVHelper for exporting inventory data | MUST HAVE |  | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Implement EmailService to send reports via SMTP | MUST HAVE |  | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Add “Generate Report” option in Admin Menu | SHOULD HAVE | US-11 | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Integrate DB + CSV + Email modules for full reporting | MUST HAVE | US-4,US-11,US-10 | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Implement OTP-based user verification during registration | SHOULD HAVE |  | All Students | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Add “Verify Email” & “Resend OTP” options in main menu | COULD HAVE |  | All Students | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Implement stock monitoring logic for low-stock alerting | MUST HAVE |  | All Students | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Develop and schedule automated stock alert generator | MUST HAVE |  | All Students | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Integrate email notifications for low-stock products | MUST HAVE |  | All Students | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Package and deploy full inventory management system | MUST HAVE |  | All Students | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.